## Agile Sprint Backlog Group 3
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 13
Update GUI to have perimter as option |  | John | Complete | 3 | 0 | 1 | 1 | 0 | 1 | 0
Multiple Options in GUI |  | John | Complete | 5 | 1 | 1 | 1 | 1 | 1 | 1
Implement sending emails |  | John | In Progress | 5 | 0 | 1 | 1 | 2 | 0 | 0
Task
User Story #2 | 15
Learn Google ApI |  | Emily | Complete | 5 | 0 | 1 | 1 | 1 | 1 | 1
Attach Google API to code |  | Emily | In Progress | 5 | 1 | 1 | 2 | 1 | 0 | 0
Attach the perimter option to GUI |  | Emily | Complete | 5 | 1 | 2 | 1 | 0 | 1 | 0
Task
User Story #3 | 12
Build UML |  | Isaac | Complete | 3 | 1 | 1 | 0 | 0 | 1 | 0
Double check the GUI |  | Isaac | Complete | 4 | 1 | 1 | 0 | 1 | 1 | 0
Edit the UML |  | Isaac | Complete | 5 | 1 | 2 | 1 | 2 | 1 | 1
Task
User Story #4 | 15
Build Gui |  | Jarod | Complete | 6 | 1 | 2 | 1 | 1 | 1 | 0
Redo the Sprint Backlog |  | Jarod | In Progress | 4 | 1 | 0 | 1 | 0 | 0 | 0
Merge both GUI from sprints |  | Jarod | Complete | 5 | 1 | 1 | 1 | 1 | 0 | 0
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 55 | 46 | 32 | 21 | 11 | 3 | 0